## Handover checklist
Unit handover checklist
19 points, in four groups. Project Audit Pro · projectauditpro.com · free to use and to change
Project |  |  | Unit
A unit is ready when every applicable point is done or explained. Anything marked N/A needs a reason beside it.
Group | No. | Check | What it means | Done | N/A | Evidence / note | By | Date
Quality | 1 | All inspection & test plans signed off for this unit | Every applicable ITP stage recorded as Pass or N/A
Quality | 2 | Snagging inspection complete, all snags closed | Two-stage close: fixed by the trade, then verified by you
Quality | 3 | No open non-conformances against this unit | All NCRs closed with verification evidence
Quality | 4 | Pre-handover clean complete | Builders clean and sparkle clean signed off
Records | 5 | O&M manual / home user guide issued | Appliance manuals, warranties, product data
Records | 6 | Asset and warranty register updated for this unit | Serial numbers and warranty start dates captured
Records | 7 | As-built drawings and services layouts issued | Including concealed services routes
Records | 8 | Golden thread records uploaded (HRB only) | Building Safety Act 2022 — mandatory for higher-risk buildings
Statutory | 9 | Electrical Installation Certificate (BS 7671) issued | EIC plus schedule of test results, competent-person scheme cert
Statutory | 10 | Gas safety / heating commissioning certificate issued | Where applicable — Gas Safe or unvented cylinder cert (G3)
Statutory | 11 | Water services flushed, tested and chlorinated | Pressure test and sampling records held
Statutory | 12 | Fire alarm / detection commissioned and certified | BS 5839-6 grade and category recorded
Statutory | 13 | Ventilation commissioned and airflow rates recorded | Part F commissioning sheet per dwelling
Statutory | 14 | Fire-stopping and compartmentation verified | Photographic register of penetrations, third-party inspected
Statutory | 15 | Air tightness / Part L evidence available | As-built SAP and BREL report where applicable
Handover | 16 | Keys, fobs and meter readings recorded | Key numbers issued and signed for
Handover | 17 | Utilities live and accounts transferred | Electric, water, comms references confirmed
Handover | 18 | Resident demonstration completed | Heating, ventilation, alarm, appliance walkthrough
Handover | 19 | Defects liability period and reporting route explained | Contact details and response times issued in writing
|  | Points marked done |  | 0
Handed over by |  |  |  | Date
Received by |  |  |  | Date