## NCR
Non-conformance report
Project Audit Pro · projectauditpro.com · free to use and to change
One report per non-conformity. Shaded cells are yours to fill in. A correction puts this occurrence right; a corrective action stops it happening again — they are not the same field and should not say the same thing.
Identification
NCR number
Date raised
Raised by
Project
Location / unit
Work package
Responsible organisation
Severity | Minor, Major or Critical
1 · Description of the non-conformity
Description | What was found, where, and when
2 · Requirement not met
Requirement | The clause, drawing or standard it fails against
3 · Impact assessment
Impact | On the works, the programme, adjacent trades and safety
4 · Disposition and root cause
Agreed disposition | See the Lists sheet
Root cause | See the Lists sheet
Approved by
Date approved
5 · Correction and corrective action
Correction — this occurrence
Corrective action — to prevent recurrence
Action owner
Target completion
6 · Verification and close-out
Verification evidence | Photographs, test results, re-inspection
Closed by | Never the party that carried out the correction
Date closed

## Lists
Lists
The values the form above expects.
Dispositions | Root causes | Statuses | Severity
Rework | Workmanship | Open | Minor
Repair | Supervision | Disposition set | Major
Replace | Design / information | Action in progress | Critical
Use as-is (concession) | Material or product | Awaiting verification
Further testing / investigation | Setting out / survey | Closed
Remove and reconstruct | Sequencing / programme | Void
Competence / training
Damage by others
Not yet determined

## Register
NCR register
One line per report, so the open ones can be counted.
NCR | Date | Title | Location | Responsible organisation | Severity | Disposition | Root cause | Status | Target | Closed
NCR-001 | 2026-09-23 | Compartment wall not sealed at riser | Block B · Level 03 | Ridgeway M&E | Major | Rework | Supervision | Corrective action | 2026-10-03