## Snagging list
Snagging list
Project Audit Pro · projectauditpro.com · free to use and to change
One defect per row. Describe the defect, not the fix. An item is closed by somebody other than the trade that fixed it — hence two sets of columns at the end. Row 7 is an example; delete it.
Ref | Date raised | Block / level | Unit | Room / element | Defect | Severity | Priority | Trade / subcontractor | Target date | Status | Photo | Fixed by | Date fixed | Closed by | Date closed
SNG-001 | 2026-09-23 | Block B · Level 02 | Flat 12 | Kitchen | Worktop join at the sink run is open and unsealed | Moderate | Medium | Ridgeway Joinery | 2026-10-07 | Open | Yes

## Summary
Where the list stands
Counts follow the list; nothing to fill in here.
Status | Items
Open | 1
In progress | 0
Fixed - to check | 0
Closed | 0
Rejected | 0
Total raised | 1